## InChI v. 1.05
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Info/Ice-box/to be considered | min.......med....Most EFFORT |  |  |  |  | green,yellow,orange | 18 | https://trello.com/c/ToM4Il6k
Info/Ice-box/to be considered | Most......med.....min IMPORTANT |  |  |  |  | blue,purple,red | 19 | https://trello.com/c/JGHpUA0L
Info/Ice-box/to be considered | Nicklaus/Guasch tautomers paper | ---------- Forwarded message ---------- From: *Igor Pletnev* <igor.pletnev@gmail.com> Date: Tuesday, October 11, 2016 Subject: Nicklaus/Guasch tautomers paper To: igor.pletnev@gmail.com http://pubs.acs.org/doi/pdf/10.1021/acs.jcim.6b00338 |  |  |  |  | 20 | https://trello.com/c/3O5r7e5M
Info/Ice-box/to be considered | ** NOT FOR PRE-RELEASE ** Write to Ruchard to publish RelNotes.pdf stand-alone (not in archive) |  |  |  |  | blue,green | 13 | https://trello.com/c/9W9foTz3
Info/Ice-box/to be considered | Use ftell/fseek for file reads? |  |  |  |  | yellow,blue | 38 | https://trello.com/c/F9EyGIbY
Product backlog | AuxInfo->InChI for polymers |  |  |  |  | red,yellow | 10 | https://trello.com/c/5XpzyPXM
Product backlog | Enable (H,H) for SRU, in addition to (*, *) |  |  |  |  | yellow,purple | 30 | https://trello.com/c/FU1ySmiz
Product backlog | inchi2inchi for polymers - made work normally (currently a stub) |  |  |  |  | red,orange | 9 | https://trello.com/c/o0EEAqbA
Product backlog | Make all file reads (besides those V3000) via growing buffer rather than array{MAX...LEN] |  |  |  |  | blue,orange | 11 | https://trello.com/c/YZrJPxao
Product backlog | Eliminating a non-stereo marked as stereo | ---------- Forwarded message ---------- From: Tchekhovskoi, Dmitrii V. Dr. (Fed) <dmitrii.tchekhovskoi@nist.gov> Date: Mon, Nov 21, 2016 at 3:10 PM Subject: RE: InChI v.1.05, beta-testing To: Igor Pletnev <igor.pletnev@gmail.com> Dear Igor, Unfortunately I was not able to do more testing. There is a long standing problem of eliminating a non-stereo marked as stereo, which needs (a new?) theoretical consideration because the current approach does not seem to work there. So far I could not make it. Perhaps you can. An example of (in my opinion) false double bond stereo is attached. Best regards Dima. *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com] *Sent:* Friday, November 11, 2016 9:47 AM *To:* Tchekhovskoi, Dmitrii V. Dr. (Fed) <dmitrii.tchekhovskoi@nist.gov> *Subject:* InChI v.1.05, beta-testing Dear Dima, hope you are doing well. Have you had time to look in more details at InChI software beta v. 1.05? Seems that beta-testing period is ending, so I am going to finally incorporate the necessary fixes (there were some useful bug reports in inchi-discuss and in my own e-mail correspondence)... Best wishes, Igor |  |  |  | orange,blue | 54 | https://trello.com/c/Na3AO2cK
Pre-release: bugs reported | **T024** Do what Burt Leland nicely pointed out to, "source file cleanup in updated of InChI software version 1.05" | ---------- Forwarded message ---------- From: Burt Leland <bleland@eyesopen.com> Date: Wed, Jan 4, 2017 at 8:44 PM Subject: RE: [InChI-discuss] What is changed in updated pre-release of InChI software version 1.05 To: Igor Pletnev <igor.pletnev@gmail.com> Igor, Not to be too “nit-picky”, but could you do a source file cleanup prior to the next/final release? e.g., unix line endings (any reasonable editor on windows OTHER than NotePad can handle these nicely), eg via dos2unix.exe remove end-of-line extraneous blanks convert mixed tab/space usage to space only ensure a blank line at end of all source files (some compilers complain about this for pedantic warning levels) *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com] *Sent:* Tuesday, January 3, 2017 8:58 AM *To:* Alan McNaught <mcnaught@ntlworld.com> *Cc:* inchi-discuss@lists.sourceforge.net; Keith T Taylor <keith.taylor@ laderaconsultancy.com> *Subject:* [InChI-discuss] What is changed in updated pre-release of InChI software version 1.05 Dear all, let me briefly summarize what is changed in the updated pre-release. Updates account for the issues reported during the first round of beta-testing; all the critical and nearly all other reported issues were fixed. Some other fixes were introduced in the course of additional internal testing. Main issues/corresponding changes to initial pre-release: - gcc requires explicit casts of void* to the result of inchi_calloc (Evan Bolton, 2016-10-08); - technical manual needs updating, polymers (John May, 2016-10-10); - GetINCHI bug - 0D stereo is not passed (Noel O'Boyle, 2016-10-10); - fix status check from GetStructFromINCHIEx() and several other minor code alterations; (patch submitted by Burt Leland, 2016-10-10); - some warnings during compilation using gcc 6.2.1 (Dominik Mierzejewski, 2016-10-11); - change to (minimally) allow OSX linking (Burt Leland, 2016-10-11); - possible empty loop in runichi3.c (Peter Linstrom, 2016-10-13); - minor bug in /OUTPUTSDF mode, inchi-1 exec (Dmitrii Tchekhovskoi, 2016-10-13); - couple of problems in reading V3000-format and treating large structures (Keith Taylor, 2016-11-03, 2016-11-28); - crash (seg fault under Linux) on InChI2Struct conversion for particular InChI string (Michal Nowotka, 2016-12-16); - several issues found on additional internal testing, especially concerning treatment of polymers and large molecules (2016-10 to 2016-12). We are deeply grateful to all who partcipated (and those who will participate) in beta-testing, in particular: Evan Bolton, Burt Leland, Peter Linstrom, John May, Dominik Mierzejewski, Michal Nowotka, Noel O'Boyle, Keith Taylor, Dmitrii Tchekhovskoi, Paul Thiessen, Xing Gao, and others. Happy New Year! Regards, Igor On Tue, Jan 3, 2017 at 1:23 AM, Alan McNaught <mcnaught@ntlworld.com> wrote: As a result of comments on the pre-release version of InChI software version 1.05 some changes have been made, and a further version is submitted for your consideration at http://www.inchi-trust.org/downloads105/. If you have any further comments please send them by Tuesday January 10th. Happy New Year Alan McNaught ************************************************************* Dr A D McNaught Secretary, InChI Trust www.inchi-trust.org Secretary, IUPAC Division VIII InChI Subcommittee http://iupac.org/who-we-are/divisions/division-details/?body_code=802 8 Cavendish Avenue Cambridge CB1 7US, UK e-mail: mcnaught@ntlworld.com ************************************************************* ------------------------------------------------------------ ------------------ Check out the vibrant tech community on one of the world's most engaging tech sites, SlashDot.org! http://sdm.link/slashdot _______________________________________________ InChI-discuss mailing list InChI-discuss@lists.sourceforge.net https://lists.sourceforge.net/lists/listinfo/inchi-discuss |  |  |  | yellow,purple | 65 | https://trello.com/c/npXnq72H
Pre-release: bugs reported | **T023** Issues by Dalke/InChI-discuss - Jan 3 2017 and November 29, 2014 (!), on handling aliases in Molfile | ---------- Forwarded message ---------- From: Andrew Dalke <dalke@dalkescientific.com> Date: Thu, Jan 5, 2017 at 2:37 AM Subject: Re: [InChI-discuss] What is changed in updated pre-release of InChI software version 1.05 To: Igor Pletnev <igor.pletnev@gmail.com> Cc: "inchi-discuss@lists.sourceforge.net" < inchi-discuss@lists.sourceforge.net> On Jan 3, 2017, at 4:57 PM, Igor Pletnev <igor.pletnev@gmail.com> wrote: > Updates account for the issues reported during the first round of beta-testing; all the critical and nearly all other reported issues were fixed. Some other fixes were introduced in the course of additional internal testing. On November 29, 2014 I reported a few likely problems. The emails were titled: - "likely incorrect handling of atom alias", where a meaningless atom alias like "PH4d" is parsed as "PdH4". (In general, toolkits like the RDKit do not handle aliases in the same way as InChI, which means they may generate different InChI strings for the same molfile input.) - "too high valence flag causes segfault", where a line like 0.0000 0.0000 0.0000 K 0 0 0 0 0 80 0 0 0 0 0 0 causes the InChI binary to segfault. - "segfault bad atom alias", combines both of those, where an alias like "T79K" causes the binary to segfault. I just tested with the preview release of 1.05 and found that these still exist. (I also reported a problem for a hydrogen isotope with too large of a mass difference. That appears to have been fixed.) Reproducibles are attached: % grep --before 2 --after 1 "^A " atom_alias.sdf 1 0 0 0 0 0 999 V2000 0.0000 0.0000 0.0000 C 0 0 0 0 0 0 0 0 0 0 0 0 A 1 PH4d % ../../bin/Linux/inchi-1 -STDIO < atom_alias.sdf 2> /dev/null ¦ grep InChI InChI=1S/Pd.4H (In the RDKit, this same SD file is interpreted as a methane: >>> from rdkit import Chem >>> s = open("atom_alias.sdf").read() >>> mol = Chem.MolFromMolBlock(s) >>> Chem.MolToInchi(mol) 'InChI=1S/CH4/h1H4' ) % ../../bin/Linux/inchi-1 -STDIO < bad_valence.sdf 2> /dev/null Segmentation fault: 11 % ../../bin/Linux/inchi-1 -STDIO < too_high_valence_in_alias.sdf 2> /dev/null Segmentation fault: 11 The segmentation faults occur with both gcc-6.2 and clang-800.0.42.1 . I suspect that any program which uses the new MakeINCHIFromMolfileText() API instead of its own molfile parser will similarly segfault. Regards, Andrew dalke@dalkescientific.com |  |  |  | blue,yellow | 63 | https://trello.com/c/mhQb2wK8
Pre-release: bugs reported | **T023b** "too high valence flag causes segfault" (Dalke, part of T023 ) | [5 empty] | 67 | https://trello.com/c/njTjwMrw
Pre-release: bugs reported | **T023c** segfault bad atom alias (Dalke, part of T023 ) | [5 empty] | 68 | https://trello.com/c/k9PEnpnq
Pre-release: bugs reported | **T006** Return #define INCHI_DECL __stdcall for Win32 dll, as per ACD/Labs request "for back-compatibility" | ---------- Forwarded message ---------- From: *Igor Pletnev* <igor.pletnev@gmail.com> Date: Tuesday, October 11, 2016 Subject: InChI v. 1.05 - первые плоды To: Andrey Yerin <erin@acdlabs.ru> Cc: Dmitry Redkin <redkin@acdlabs.ru> Андрей - к финальному релизу я верну, конечно (не пишу 100% только потому, что окончательно отучился так писать:) Просто буду делать это в пакете со всей прочей "работой над ошибками", с тестированием, блэкджеком и т.п. Если во время бета тестирования (т.е. до начала ноября) вам не критично - лучше вообще использовать 64-битную сборку. Если критично - пропатчьте от руки (пишу ниже как, но Дмитрий и сам знает:) #define INCHI_DECL надо поменять на #define INCHI_DECL __stdcall в INCHI_BASE\src\inchi_api.h libinchi\src\inchi_dll_a.h Всего, Игорь 2016-10-11 18:04 GMT+03:00 Andrey Yerin <erin@acdlabs.ru <javascript:_e(%7B%7D,'cvml','erin@acdlabs.ru');>>: > Спасибо. > Т.е. есть надежда вернуть или лучше таки переделать? > И да, мы ретроградно все еще работаем и с 32-битными приложениями. > > АЕ > > On 11.10.2016 17:58, Igor Pletnev wrote: > >> Привет и спасибо! >> >> Я сам крайне удивился... >> >> Короткое расследование показало, что мистическое исчезновение __stdcall >> произошло при инкорпорировании большого куска стороннего кода (определения >> экспортируемых функций тем гражданам трогать никак не полагалось, но... в >> общем, недостаточно "следили за руками", сами виноваты :( >> >> Постараюсь в скором времени все вернуть назад. >> >> (Кстати, вы первые это заметили! Похоже, народные массы таки пересели на >> Win 64-bit, где все-равно один __fastcall :) >> >> Всего, >> Игорь >> >> >> > > -- > This message has been scanned for viruses and > dangerous content by MailScanner, and is > believed to be clean. > > |  |  |  | yellow,red | 33 | https://trello.com/c/9OH1Cfm1
Pre-release: bugs reported | **T009b** Remaining minor issues on "Warnings during compilation (using gcc 6.2.1)", by Dominik 'Rathann' Mierzejewski | **T009** ---------- Forwarded message ---------- From: *Dominik 'Rathann' Mierzejewski* <dominik@greysector.net> Date: Tuesday, October 11, 2016 Subject: InChI Software version 1.05 To: inchi-discuss@lists.sourceforge.net Dear Alan, On Thursday, 06 October 2016 at 10:52, Alan McNaught wrote: > InChI Software version 1.05 is now available for review, from the InChI > Trust website: > > http://www.inchi-trust.org/downloads105/ [...] > Comments by Friday November 4th, please. There are a lot of warnings during compilation (using gcc 6.2.1), some of which might indicate programming errors and may lead to crashes. For example: ../../../../INCHI_BASE/src/runichi3.c: In function 'OrigAtData_FillAtProps': ../../../../INCHI_BASE/src/runichi3.c:2455:9: warning: this 'for' clause does not guard... [-Wmisleading-indentation] for (i=0; i<nrings; i++); ^~~ ../../../../INCHI_BASE/src/runichi3.c:2456:9: note: ...this statement, but the latter is misleadingly indented as if it is guarded by the 'for' { ^ This looks like an unintended ';' at the end of line 2455. There are several warnings about implicit declaration of memicmp, which mean missing #include "ichicomp.h". Another example: ./src/e_0dstereo.c: In function 'set_0D_stereo_parities': ../src/e_0dstereo.c:2744:15: warning: 'rmin' may be used uninitialized in this function [-Wmaybe-uninitialized] if ( rmin / rmax < MIN_SINE ) { ~~~~~^~~~~~ ../src/e_0dstereo.c:2629:34: note: 'rmin' was declared here double bond_len_xy[4], rmax, rmin; ^~~~ ../src/e_0dstereo.c:2744:15: warning: 'rmax' may be used uninitialized in this function [-Wmaybe-uninitialized] if ( rmin / rmax < MIN_SINE ) { ~~~~~^~~~~~ ../src/e_0dstereo.c:2629:28: note: 'rmax' was declared here double bond_len_xy[4], rmax, rmin; ^~~~ This might lead to a division by 0 if rmax is 0. rmax and rmin will be 0 if j1 is 0 (line 2730). j1 will be 0 if at[cur_at].num_bonds is 0 (line 2698). I don't know if the last case is possible, but neither does gcc. There are many more and I'm attaching a more complete log of inchi build from Fedora. I patched the Makefile to allow setting compiler flags from the command line. Regards, Dominik -- Fedora http://fedoraproject.org/wiki/User:Rathann RPMFusion http://rpmfusion.org "Faith manages." -- Delenn to Lennier in Babylon 5:"Confessions and Lamentations" |  |  |  | yellow,purple | 61 | https://trello.com/c/3o5rkoNV
Pre-release: bugs reported | **T011** InChI error examples - Burt Leland "for your backlog" (round-tripping through ChEMBL-18) | **T011** ---------- Forwarded message ---------- From: Burt Leland <bleland@eyesopen.com> Date: Sat, Oct 15, 2016 at 1:13 AM Subject: InchI error examples for your backlog (ChEMBL-18) To: Igor Pletnev <igor.pletnev@gmail.com> These from ChEMBL_18 – current release is ‘22’ ftp://ftp.ebi.ac.uk/pub/databases/chembl/ChEMBLdb/releases/chembl_22/ Number of InChI strings validated = 1,352,681 inchi-1.exe chembl_18.inchi_failures.sdf chembl_18.inchi_failures.out chembl_18.inchi_failures.log NUL /FixedH /RecMet /AuxNone inchi-1.exe chembl_18.inchi_failures.out chembl_18.inchi_failures.IO.out chembl_18.inchi_failures.IO.log NUL /Inchi2Struct /FixedH /RecMet /AuxNone There are some structures with no errors/warnings, I didn’t filter these out – looks like *1178* structures and *1143* warning messages. Looks like 0.084% error rate – pretty respectable! Hadn’t seen this yet, 1153: ; *Conversion failed on component(s) F1(C31H34N4) Most are one of these you indicated previously, 1155: Problems/mismatches: Fixed-H( …. 1156: Problems/mismatches: Mobile-H( … 1171: (Metal compound); … I verified all the smiles strings round-trip to the identical smiles (ie ChEMBL smiles isn’t busted), and that the smiles strings round-trip to the same smiles for SMI->SDF->SMI, so the SDF and SMI should be 100% in synch. |  |  |  | yellow,blue | 41 | https://trello.com/c/HcpqCXFF
Pre-release: bugs reported | Bug reported by David Sharpe in [InChI-discuss] - "Double bond stereoperception dependant on precence of remote atoms with non-standard valence" | ---------- Forwarded message ---------- From: David Sharpe <sharped@rsc.org> Date: Fri, Dec 23, 2016 at 4:26 PM Subject: [InChI-discuss] Double bond stereoperception dependant on precence of remote atoms with non-standard valence To: "inchi-discuss@lists.sourceforge.net" < inchi-discuss@lists.sourceforge.net> Hi, Apologies if what I am reporting is a known issue/feature – I couldn’t find this in the Archive. I was looking at generating the InChI for the molecule shown in the following Wikipedia article: https://en.wikipedia.org/wiki/ Malvidin-3-O-(6-p-coumaroyl)glucoside And noticed that the structure when drawn with the trans- geometry in the coumaroyl group generates an InChI that does not have the double bond geometry encoded (no \b layer) Eg. InChI=1S/C32H30O14/c1-41-22-9-16(10-23(42-2)27(22)37)31-24( 13-19-20(35)11-18(34)12-21(19)44-31)45-32-30(40)29(39)28(38) 25(46-32)14-43-26(36)8-5-15-3-6-17(33)7-4-15/h3-13,25,28-30, 32,38-40H,14H2,1-2H3,(H3-,33,34,35,36,37)/p+1/t25-,28-,29+,30-,32-/m1/s1 Having found this when using ACD/ChemSketch – I then decided to check using just the InChI algorithm and started using the winchi-1.exe (version 1.04 File version 1.0.4.1) running on windows 7, with the default settings. When I generated the InChI from my SDF file I obtained the same InChI as I had from ChemSketch For completeness I also tested with a structure with the cis-geometry and with an undefined geometry – and in all 3 cases found that the same InChI is generated. Based on this I then started to add test cases to narrow down what features of the molecule cause the /b layer not to be generated – I can supply an SDF file of these upon request. My findings seem to be that the issue is caused when the structure has both a double bond with conjugation to other groups, and also an atom that has a ‘non-standard’ valence (that does not result from protonation) (Eg Oxonium, sulfonium, phosphonium, ammonium) within the same covalently linked framework. While I don’t know how much to read into the following observation: it is interesting to note that when comparing: the original glucoside and the structure obtained by “reducing” the oxonium to an ether ( -O+= à -O- ), in the winInChI.exe interface. When compared the rendering of the former seems to show the double bond and carbonyl of the coumaroyl group as being a part of an extended mobile/tautomeric system, whereas in the latter that is not the case. My guess is that the presence of the oxonium species the triggers a function to identify mobile groups that is being applied to the whole of the structure and has an unexpected effect on other functionalities that would not normally be considered as part of the tautomer model. Having kind of worked out what the issue is, as I wrote this email, I have 2 questions: 1. Is my analysis correct? 2. Is there any way to avoid the inconsistency that this introduces regarding perception of double bond geometry when generating an InChI? Season’s Greetings and king regards, Dave *Dr David Sharpe, AMRSC* Royal Society of Chemistry, Thomas Graham House, Science Park, Milton Road, Cambridge, CB4 0WF, UK Tel +44 (0) 1223 432135 [image: QA_InternationalTrade2013] <http://www.rsc.org/AboutUs/News/PressReleases/2013/RSC-wins-Queens-Award-for-Enterprise.asp> *ChemSpider* <http://www.chemspider.com/> – Search and share chemistry *Access ChemSpider anytime, anyplace, anywhere with the free ChemSpider mobile **app* <http://itunes.apple.com/us/app/chemspider/id458878661?mt=8> DISCLAIMER: This communication (including any attachments) is intended for the use of the addressee only and may contain confidential, privileged or copyright material. It may not be relied upon or disclosed to any other person without the consent of The Royal Society of Chemistry. If you have received it in error, you must not copy or show it to anyone; please contact us immediately by replying to this email and highlighting the error. Any advice given by The Royal Society of Chemistry has been carefully formulated but is necessarily based on the information available, and The Royal Society of Chemistry cannot be held responsible for accuracy or completeness. In this respect, any views or opinions presented in this email are solely those of the author and may not represent those of The Royal Society of Chemistry. The Royal Society of Chemistry owes no duty of care and shall not be liable for any resulting damage or loss as a result of the use of this email and/or attachments. The Royal Society of Chemistry acknowledges that a disclaimer cannot restrict liability at law for personal injury or death arising through a finding of negligence. The Royal Society of Chemistry does not warrant that its emails or attachments are Virus-free: Please rely on your own screening. The Royal Society of Chemistry is a charity, registered in England and Wales, Number 207890, and a company incorporated in England by Royal Charter (Registered No. RC000524) Registered office: Burlington House, Piccadilly, London W1J 0BA, Telephone: 0207 4378 6556, Facsimile: 0207 4490 3393 (Head Office). ------------------------------------------------------------ ------------------ Developer Access Program for Intel Xeon Phi Processors Access to Intel Xeon Phi processor-based developer platforms. With one year of Intel Parallel Studio XE. Training and support from Colfax. Order your platform today.http://sdm.link/intel _______________________________________________ InChI-discuss mailing list InChI-discuss@lists.sourceforge.net https://lists.sourceforge.net/lists/listinfo/inchi-discuss |  |  |  |  | 64 | https://trello.com/c/4wTKEMeh
SourceForge bug tracker | **T119** #19 Error in auxinfo original atom order when hydrogen isotopes present | **T119** #19 Error in auxinfo original atom order when hydrogen isotopes present Milestone: v1.0 (example) Status: open Owner: nobody Labels: None Priority: 5 Updated: 2016-10-10 Created: 2016-10-10 Creator: Noel O'Boyle Private: No Dear InChI developers, I'm trying to use the InChi and auxiliary information to work out the original atom order in the input. In general it works, but I've come across an exception. If I convert the SMILES string CC[2H] (or its associated SDF file - attached) to an InChI I have: InChI=1S/C2H6/c1-2/h1-2H3/i1D AuxInfo=1/0/N:1,2/E:(1,2)/rA:3CCH.i2/rB:s1;s2;/rC:;;; In the input, the Deuterium was attached to the second atom ("atom 2"). In the InChI, D is attached to atom 1. So...I would expect the normalised order to be /N:2,1 But the normalised order is actually /N:1,2 This is causing me some problems, so I hope that this is a bug. Otherwise, I think it means that it is not possible to recreate the input order in certain cases involving hydrogen isotopes (or is there something I'm missing here). Regards, Noel (reposted from a mail to the mailing list on 2011/12/12) 1 Attachments tmp.sdf Discussion |  |  |  | yellow,red | 48 | https://trello.com/c/d8JEYTJq
SourceForge bug tracker | **T118** #18 Different InChIs dependent on atom input order |  |  |  |  | orange,red | 49 | https://trello.com/c/nw9fAFXs
SourceForge bug tracker | **T117** #17 A round-trip to InChI API changes the InChI | #17 A round-trip to InChI API changes the InChI Status: open Owner: nobody Labels: None Priority: 5 Updated: 2011-01-28 Created: 2011-01-28 Creator: Anonymous Private: No I encountered an issue with InChI API when processing PubChem Compound 10775979. Using the SDF downloaded from PubChem website and the InChI Windows binary distribution, I was able to get the following InChI string: InChI=1S/C11H11N3O3/c1-6-4-3-5-8(7(6)2)14-9(10(12)15)11(16)17-13-14/h3-5H,1-2H3,(H2-,12,13,15,16) This is consistent with the InChI string embedded in the PubChem SDF. I then use the C++ program [source attached below] to test whether InChI API was able to correctly parse the InChI string into a molecule and then get back the same InChI string. The program calls GetStructFromINCHI with the above InChI string, and gets back a molecule structure. It then passes this structure to the GetINCHI function get back an InChI string. This round trip to the InChI API should give the same InChI as above. Unfortunately, it alters the InChI string slightly and gives the following: InChI=1S/C11H11N3O3/c1-6-4-3-5-8(7(6)2)14-9(10(12)15)11(16)17-13-14/h3-5H,1-2H3,(H2-,12,15,16) The C++ program is listed below: // InChI round trip test #include <inchi_api.h> #include <iostream> int main() { // inchi to mol char inchi[] = "InChI=1S/C11H11N3O3/c1-6-4-3-5-8(7(6)2)14-9(10(12)15)11(16)17-13-14/h3-5H,1-2H3,(H2-,12,13,15,16)"; inchi_InputINCHI inchiInput; inchiInput.szInChI = inchi; inchiInput.szOptions = NULL; // output structure inchi_OutputStruct inchiOutput; // DLL call GetStructFromINCHI(&inchiInput, &inchiOutput); // mol to inchi // create input inchi_Input input; input.atom = inchiOutput.atom; input.stereo0D = inchiOutput.stereo0D; input.szOptions = NULL; input.num_atoms = inchiOutput.num_atoms; input.num_stereo0D = inchiOutput.num_stereo0D; // create output inchi_Output output; // call DLL GetINCHI(&input, &output); std::cout << output.szInChI << std::endl; return 0; } Discussion |  |  |  | purple,yellow | 50 | https://trello.com/c/CxB2YC0W
SourceForge bug tracker | **T116** #16 InChI's with hydrogen for single atoms | #16 InChI's with hydrogen for single atoms Status: open Owner: nobody Labels: None Priority: 5 Updated: 2010-10-25 Created: 2010-10-25 Creator: pmatos Private: No Hi, We are developing the ChEBI database and need to model atoms. When we generate an InChI for a Lithium atom from the following molfile we get InChI=1/Li.H. It adds an extra hydrogen? " Marvin 12070515392D 1 0 0 0 0 0 999 V2000 0.0000 0.0000 0.0000 Li 0 0 0 0 0 0 0 0 0 0 0 0 M END " However when we generate an InChI for Cobalt by replacing Li with Co in the above file we get InChI=1/Co. There is no hydrogen generated. Can you explain the discrepancy. Cheers, Paula Discussion |  |  |  | purple,green | 52 | https://trello.com/c/6yQDf4cq
SourceForge bug tracker | **T115** #15 Different InChIs generated if atoms are swapped in a bond | #15 Different InChIs generated if atoms are swapped in a bond Status: open Owner: nobody Labels: None Priority: 5 Updated: 2010-04-22 Created: 2010-04-22 Creator: Jörg-Rüdiger Hill Private: No The InChI generated depends on the order of the atoms in bond definitions. The attached test cases differ only by the atom order in four bonds. In one case the bond is defined, for example, as C5-H11 in the other as H11-C5. The file input.mol produces: 1S/C3H8O2/c1-2-3(4)5/h3-5H,2H2,1H3, the file output.mol: 1S/C3H6O2/c1-2-3(4)5/h2H2,1H3,(H,4,5). Discussion Jörg-Rüdiger Hill Jörg-Rüdiger Hill - 2010-04-22 The first structure input.mol Jörg-Rüdiger Hill Jörg-Rüdiger Hill - 2010-04-22 The second structure output.mol |  |  |  | green,purple | 51 | https://trello.com/c/wGUbOer3
SourceForge bug tracker | **T114** #14 Preprocessing depends on order atoms are defined | #14 Preprocessing depends on order atoms are defined Status: open Owner: nobody Labels: None Priority: 5 Updated: 2010-03-10 Created: 2010-03-10 Creator: Timo Böhme Private: No The preprocessing step in standard InChI (1.02) creation which normalizes hydrogens etc. depends on the order in which atoms are defined in input structure. The attached test cases demonstrate this. The structure in test case 1 (which is a substructure of PubChem CIS 3353305) produces InChI=1S/C4H7N5O2/c5-8-2-3(10)7-1-4(11)9-6/h2,5-7,10H,1H2/b3-2- whereas in test case 2 we get InChI=1S/C4H6N5O2/c5-8-2-3(10)7-1-4(11)9-6/h2,6-7,10H,1H2/q-1/p+1/b3-2- (one hydrogen removed by preprocessing). Both test cases (SDF files) differ only in the order atoms are defined. In test case 2 the charged Oxygen is moved from last to first position in atom block and bond atom numbers are updated accordingly. Thus both test cases describe the same molecule but get different standard InChIs. Timo Discussion Timo Böhme Timo Böhme - 2010-03-10 test case 1: all hydrogens remain in InChI testCase.sdf Timo Böhme Timo Böhme - 2010-03-10 test case 2: preprocessing removes one Hydrogen testCase_movedAtom.sdf |  |  |  | yellow,red | 53 | https://trello.com/c/LSENa5EB
Pre-release: feature requests | **T014** Recognize polymer SRU even if no SBL line [by bonds to * and in src-based form] (Andrey Erin) | **T014** |  |  |  | purple,yellow | 7 | https://trello.com/c/mEgvlkJw
Pre-release: feature requests | **T012a** Is it possible to update the “UNDERIVATIZE” part to the code I gave to you previously? (DT on 2016-10-06) |  |  |  |  | blue,orange | 3 | https://trello.com/c/sp5LfpDG
Pre-release: feature requests | **T013** Make (at least as option) winchi-1 not writing log and prb files (Andrey Erin) | **T013** |  |  |  | blue,yellow | 8 | https://trello.com/c/clPTPlop
Pre-release: feature requests | ** WTH? ** Attachment points (M APO in ctab) are not handled but could be used in place of star atoms | ---------- Forwarded message ---------- From: *John M* <john.wilkinsonmay@gmail.com> Date: Monday, October 10, 2016 Subject: InChI Software version 1.05 To: inchi-discuss@lists.sourceforge.net Hi all, Some initial thoughts on the v1.05 release. I've mainly looked at polymers (in Beta) as I guess that's where most problems will be. 1) Technical manual needs updating, a section on polymers has been added but the intro says polymers are out of scope. *"Not included are polymers, molecular class representations (Markush structures), electronic states and conformations."* 2) Phase/frame shifts are not handled with capping groups, example three ways to encode poly-glycine give three different InChIs. *SMILES (click to view)* NCC(=O)NCC(=O)O ¦Sg:n:1,2,3,4:n:ht¦ pGly_1 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A1%2C2%2C3%2C4%3An%3Aht%7C%20pGly_1&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:2,3,4,5:n:ht¦ pGly_2 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A2%2C3%2C4%2C5%3An%3Aht%7C%20pGly_2&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:4,5,6,7:n:ht¦ pGly_3 > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A4%2C5%2C6%2C7%3An%3Aht%7C%20pGly_3&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> *InChI* InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-1,3,6-7(2-6,5-1) > InChIKey=YMAWOPBAYDPSLA-LCMLVUGIBA-N InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2-3,6-7(1-3,4-2) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N > InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2,4,6,8(3-6,9-4) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N 3) Different size repeats (no capping groups) don't produce comparable InChIs. Possibly out of scope but below PEG_n (odd or even) should match PEG_2n (even only), PEG_2n should not match PEG_n. I'd imagine this should be possible with more layers within the polymer layer... *CCO* ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCOCCO* > ¦Sg:n:1,2,3,4,5,6:n:ht,$_AP1;;;;;;;_AP1$¦ PEG_2n > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCOCCO*%20%7CSg%3An%3A1%2C2%2C3%2C4%2C5%2C6%3An%3Aht%2C%24_AP1%3B%3B%3B%3B%3B%3B%3B_AP1%24%7C%20PEG_2n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N > InChI=1B/C4H8O2/c1-2-6-4-3-5-1/h1-4H2/z101-1-6(1,2,1,5,2,6,3,4,3,5,4,6) > InChIKey=RYHBNJHYFVUHQT-UEXHMUNTBA-N 4) Attachment points (M APO in ctab) are not handled but could be used in place of star atoms. *CCO* ¦Sg:n:1,2,3:n:ht¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCO* > ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n_ap > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n_ap&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N InChI=1B/C2H6O/c1-2-3/h3H,2H2,1H3/z200-1-3 > InChIKey=LFQSCWFLJHTTHZ-DJNVOPQRBA-N - John |  |  |  | yellow,purple | 24 | https://trello.com/c/nxHeJu7D
Pre-release: feature requests | Check (and fix wherever possible) SourceForge ** easy ** bug tracker tickets |  |  |  |  | yellow,purple | 28 | https://trello.com/c/8V0CAyhy
Pre-release: feature requests | Check (and fix wherever possible) SourceForge ** all ** bug tracker tickets |  |  |  |  | purple,orange | 27 | https://trello.com/c/GIKc9z66
Done | **T027** GetStructFromINCHIEx() - again problems with * and Zz | ---------- Forwarded message ---------- From: Igor Pletnev <igor.pletnev@gmail.com> Date: 2017-01-19 21:00 GMT+03:00 Subject: Re: InChI v. 1.05 To: Andrey Yerin <erin@acdlabs.ru> Cc: Dmitry Redkin <redkin@acdlabs.ru> Да, это делается. "Расширенная" процедура AP IGetStructFromINCHIEx() возвращает "расширенную" структуру данных inchi_OutputStructEx, с полимерным фаршем. Собственно, только при этой обратной конвертации делается phase shift и по недо-ИЮПАКовским правилам определяется каноническая SRU с определенными связями внутри-SRU и "звездных" атомов... сама полимерная InChI из хитрости хранит все возможные варианты... Вся таблица 2 с полимерными примерами из Release Notes пропущена через /inchi2struct для контроля. Там свои хитрости, цитирую: "Table 2. Examples of InChI for polymers. Numbering follows numbers of records in the file PEX.SDF included in this distribution. Structures backconverted from InChI as follows: *restore from InChI with inchi-1 with options ‘InChI2Struct’ and ‘OutputSDF’, then import produced xyz- and stereo-less Molfile to Accelrys Draw 4.1 & make ‘Chemistry->Clean’."* Вот только это утилита командной строки inchi-1.exe, там все OK... а в API вызове GetStructFromINCHIEx() сейчас обнаружил ту же засаду со звездочками и Zz (которые должны были бы быть полностью скрыты по капотом), что вылезла у вас же позавчера при "прямом ходе". Эх, где ж вы раньше были! Поправлю и это, и завтра пришлю все вместе, чтобы не множить сущности. Да, но дальние таутомеры, однако, не бэк-конвертятся..ease это пока отложено до окончания научных опытов Марка Никлауса (сколько там геморроя будет - в обе стороны - с его новыми таутомерными правилами - я пока даже думать боюсь). ИПл 2017-01-19 18:44 GMT+03:00 Andrey Yerin <erin@acdlabs.ru>: > Игорь, а еще вопрос. > > А обратно из ИНЧИ в полимеры что-то делалось? > А то вроде пока не нашли или не поняли. > > *Соотвественно, вроде бы (раньше?) ИНЧИ с новыми таутомерами тоже обратно > не конвертились. Так и осталось? > > АЕ > > -- > This message has been scanned for viruses and > dangerous content by MailScanner, and is > believed to be clean. > > |  |  |  |  | 71 | https://trello.com/c/j2HEqzTF
Done | **T026** Polymers - GetINCHIEx - Zz vs. * problems - ACD/Labs | ---------- Forwarded message ---------- From: Dmitry Redkin <redkin@acdlabs.ru> Date: 2017-01-17 13:23 GMT+03:00 Subject: Re: InChI v. 1.05 - первые плоды To: Igor Pletnev <igor.pletnev@gmail.com>, Andrey Yerin <erin@acdlabs.ru> Игорь, привет! Попробовал передать полимеры через “старый” API ( GetINCHIEx(Inchi_InputEx) ), в частности псевдоатомы – то, что в молфайле помечается звездочкой. Звездочка не помогла. Посмотрел в исходники, поставил “Zz”.Это сработало, но мне кажется, об этом стоит упомянуть в документации (или по крайней мере добавить константу в inchiapi.h). *From:* Igor Pletnev <igor.pletnev@gmail.com> *Sent:* Tuesday, November 08, 2016 7:00 PM *To:* Andrey Yerin <erin@acdlabs.ru> *Cc:* Dmitry Redkin <redkin@acdlabs.ru> *Subject:* Re: InChI v. 1.05 - первые плоды Ага, спасибо! Ну, буду надеяться, что еще посмотрите и напишете о результатах до нашего окончательного релиза (и что ничего сверхъестественно плохого тесты не обнаружат:) Думаю, ноябрь еще весь буду возиться... > Я как-то давно это все дело невзлюбил, но наверно нужно себя заставить изучить. аналогично... ИПл 2016-11-08 18:37 GMT+03:00 Andrey Yerin <erin@acdlabs.ru>: > Привет! > > Увы, но руки не дошли. И мои и Димы :( > Текучка, да и сейчас "работаю с документами" - горит отчет по контракту. > Но очень надюсь что скоро - после 23, как вернусь, наверно будем > активничать. > > Да. я получил про R-INCHI. > Я как-то давно это все дело невзлюбил, но наверно нужно себя заставить > изучить. > > АЕ > > On 08.11.2016 16:51, Igor Pletnev wrote: > >> Андрей, Дмитрий - >> >> есть ли новости с результатами тестирования 1.05 beta? >> >> Если было время с этим еще позаниматься - напишите, пожалуйста, что так, >> что не так? >> >> В inchi-discuss >> https://sourceforge.net/p/inchi/mailman/inchi-discuss/ >> конечно, багов нарапортовали (формально период бета-тестов был до 4 >> ноября), но вроде не совсем ужасных >> >> Кстати, Андрей - должны были выложить Reaction InChI (это, слава богу, не >> моя епархия:) >> http://www.inchi-trust.org/downloads105/ >> >> (но ты должен был получить извещение уже) >> Игорь >> >> >> > > -- > This message has been scanned for viruses and > dangerous content by MailScanner, and is > believed to be clean. > > -- This message has been scanned for viruses and dangerous content by *MailScanner* <http://www.mailscanner.info/>, and is believed to be clean. -- This message has been scanned for viruses and dangerous content by *MailScanner* <http://www.mailscanner.info/>, and is believed to be clean. |  |  |  |  | 70 | https://trello.com/c/XibPjJRR
Done | **T025** Respond to Greg Landrum on 1.05 release composition/label | [5 empty] | 69 | https://trello.com/c/29zOUUdz
Done | **T0022** Michał Nowotka (@mmmnow) mentioned you in conversation on Twitter! | ---------- Forwarded message ---------- From: Richard Kidd <KiddR@rsc.org> Date: Fri, Dec 16, 2016 at 10:57 AM Subject: FW: Michał Nowotka (@mmmnow) mentioned you in conversation on Twitter! To: Igor Pletnev <igor.pletnev@gmail.com> Hi Igor Again, this one might be sorted already (or nothing to do with the InChI code) but: https://github.com/rdkit/rdkit/issues/1206 Best wishes RIchard *From:* Michał Nowotka (via Twitter) [mailto:notify@twitter.com] *Sent:* 15 December 2016 13:09 *To:* InChI_Trust *Subject:* Michał Nowotka (@mmmnow) mentioned you in conversation on Twitter! @mmmnow: @InChI_Trust Hi, this looks like a bug in the InChi library, can you please take a look? [image: Image removed by sender.] [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2F%3Frefsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=b15ad17fd420d8bce8d38514d82e7840fd9369a5&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1553> [image: Image removed by sender.] Michał Nowotka <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%2Fstatus%2F809384727492825088%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=9ea042c5ccdb4fd3dee97e2a0312b4d4aa1cb40e&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1489> mentioned you. <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%2Fstatus%2F809384727492825088%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=9ea042c5ccdb4fd3dee97e2a0312b4d4aa1cb40e&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1489> * Reply * <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fintent%2Ftweet%3Fin_reply_to%3D809384727492825088%26in_reply_to_usernames%3Dmmmnow%252CInChI_Trust%26cn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=12f0f0e582e07ebe1affdb6d17d55141abc10b34&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1281> [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=a0d1464a9d7e35efe2f34e5a3b79536251665173&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1262> *Michał Nowotka <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=a0d1464a9d7e35efe2f34e5a3b79536251665173&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1262>* @mmmnow <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=a0d1464a9d7e35efe2f34e5a3b79536251665173&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1262> Dec 15 <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%2Fstatus%2F809384727492825088%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=9ea042c5ccdb4fd3dee97e2a0312b4d4aa1cb40e&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1489> @InChI_Trust <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FInChI_Trust%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=1de56c019ebf7633a43b0fecbfcc30f7daf29bec&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1271> Hi, this looks like a bug in the InChi library, can you please take a look? github.com/rdkit/rdkit/is… <https://t.co/redirect?url=https%3A%2F%2Ft.co%2FVfu26W2wXi%3Fcn%3DbWVudGlvbg%253D%253D&t=1&cn=bWVudGlvbg%3D%3D&sig=d0380e642843bdccf95d0e6cdfc10c8086626587&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1268> [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%2Fstatus%2F809384727492825088%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=9ea042c5ccdb4fd3dee97e2a0312b4d4aa1cb40e&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1489> [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fintent%2Fretweet%3Fea_u%3D568148082%26ea_e%3D1483016932%26tweet_id%3D809384727492825088%26ea_s%3Df1c02499d1040f70828e4a97bd879d7f11ee5fc9%26cn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=b7e47770d3462285ddaba8e09bb9929b02843c15&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1279> [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fintent%2Ffavorite%3Fea_u%3D568148082%26ea_e%3D1483016932%26tweet_id%3D809384727492825088%26ea_s%3D674087556d04975c301d309d1b4aa32a7002efc0%26cn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=d84a88e1295b1decc7ed025efe21a94271234ecb&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1280> View conversation <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fmmmnow%2Fstatus%2F809384727492825088%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=9ea042c5ccdb4fd3dee97e2a0312b4d4aa1cb40e&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1489> *Settings* <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fsettings%2Fnotifications%3Fcn%3DbWVudGlvbg%253D%253D&t=1&cn=bWVudGlvbg%3D%3D&sig=afe24419811eb497864621f9fe81e076be459a95&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+27> ¦ *Help* <https://twitter.com/i/redirect?url=https%3A%2F%2Fsupport.twitter.com%3Fcn%3DbWVudGlvbg%253D%253D&t=1&cn=bWVudGlvbg%3D%3D&sig=87c181feb6b1defba67d5f6a1e5807cd347c4aee&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+97> ¦ *Opt-out* <https://twitter.com/i/u?t=1&cn=bWVudGlvbg%3D%3D&sig=b79d7235fd0eb928fb13602073500a06210c7515&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+26> ¦ *Download app* <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fdownload%3Fcn%3DbWVudGlvbg%253D%253D&t=1&cn=bWVudGlvbg%3D%3D&sig=62b7fc6c33d984b6ba5d4b3432d3da21cffab774&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+108> Twitter, Inc. 1355 Market Street, Suite 900 San Francisco, CA 94103 <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2F%3Frefsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=b15ad17fd420d8bce8d38514d82e7840fd9369a5&iid=045c80797d804d96a41f7c8fcf591a34&uid=568148082&nid=4+1553> DISCLAIMER: This communication (including any attachments) is intended for the use of the addressee only and may contain confidential, privileged or copyright material. It may not be relied upon or disclosed to any other person without the consent of The Royal Society of Chemistry. If you have received it in error, you must not copy or show it to anyone; please contact us immediately by replying to this email and highlighting the error. Any advice given by The Royal Society of Chemistry has been carefully formulated but is necessarily based on the information available, and The Royal Society of Chemistry cannot be held responsible for accuracy or completeness. In this respect, any views or opinions presented in this email are solely those of the author and may not represent those of The Royal Society of Chemistry. The Royal Society of Chemistry owes no duty of care and shall not be liable for any resulting damage or loss as a result of the use of this email and/or attachments. The Royal Society of Chemistry acknowledges that a disclaimer cannot restrict liability at law for personal injury or death arising through a finding of negligence. The Royal Society of Chemistry does not warrant that its emails or attachments are Virus-free: Please rely on your own screening. The Royal Society of Chemistry is a charity, registered in England and Wales, Number 207890, and a company incorporated in England by Royal Charter (Registered No. RC000524) Registered office: Burlington House, Piccadilly, London W1J 0BA, Telephone: 0207 4378 6556, Facsimile: 0207 4490 3393 (Head Office). |  |  |  |  | 58 | https://trello.com/c/558F58Ro
Done | **T023a* likely incorrect handling of atom alias (A. Dalke, part of T023 ) | [5 empty] | 66 | https://trello.com/c/HtHdTm0H
Done | **T022** Fix (shame, shame) issue in GetStdINCHI (like one which was in GetINCHI) | [5 empty] | 62 | https://trello.com/c/QMxl554A
Done | **T0021** Xing Gao (@XingGao123) mentioned you in conversation on Twitter! | ---------- Forwarded message ---------- From: Richard Kidd <KiddR@rsc.org> Date: Mon, Dec 12, 2016 at 12:19 PM Subject: FW: Xing Gao (@XingGao123) mentioned you in conversation on Twitter! To: Igor Pletnev <igor.pletnev@gmail.com> Hi Igor – received this bug report via twitter – seems familiar, but passing it on anyway. Best wishes Richard *From:* Xing Gao (via Twitter) [mailto:notify@twitter.com] *Sent:* 10 December 2016 10:13 *To:* InChI_Trust *Subject:* Xing Gao (@XingGao123) mentioned you in conversation on Twitter! @XingGao123: @vfscalfani @InChI_Trust bug report Function GetStructFromINCHI should be if ( ret == _IS_ERROR ¦¦ ret == _IS_FATAL ) [image: Image removed by sender.] [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2F%3Frefsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=aeb213f36b9963d03fd40048a3e379b1d1aef801&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1553> [image: Image removed by sender.] Xing Gao <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%2Fstatus%2F807528462227357696%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=bcb78f53aeefd6b7ffb3f0138ae3d35ce18bb712&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1489> mentioned you. <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%2Fstatus%2F807528462227357696%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=bcb78f53aeefd6b7ffb3f0138ae3d35ce18bb712&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1489> * Reply * <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fintent%2Ftweet%3Fin_reply_to%3D807528462227357696%26in_reply_to_usernames%3DXingGao123%252Cvfscalfani%252CInChI_Trust%26cn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=0bd8bfd1ed7aae9935159a68459a8c182bb5a618&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1281> [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=ec53d579d0e9049a41a30c41ca5a556afd7f0ce1&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1262> *Xing Gao <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=ec53d579d0e9049a41a30c41ca5a556afd7f0ce1&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1262>* @XingGao123 <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=ec53d579d0e9049a41a30c41ca5a556afd7f0ce1&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1262> Dec 10 <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%2Fstatus%2F807528462227357696%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=bcb78f53aeefd6b7ffb3f0138ae3d35ce18bb712&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1489> @vfscalfani <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fvfscalfani%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=20cbcd3e75db4ce32e0cf3df8e19aba3826caf78&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1271> @InChI_Trust <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FInChI_Trust%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=fa3896ad9c60c4439fd5f148211adf5613c5eda5&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1271> 1.0.5 bug report inchi_dll.c Function GetStructFromINCHI should be if ( ret == _IS_ERROR ¦¦ ret == _IS_FATAL ) [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%2Fstatus%2F807528462227357696%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=bcb78f53aeefd6b7ffb3f0138ae3d35ce18bb712&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1489> [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fintent%2Fretweet%3Fea_u%3D568148082%26ea_e%3D1482574363%26tweet_id%3D807528462227357696%26ea_s%3D8f263b39a5d526c0a81caf41e6476458d7d2b85a%26cn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=d17254c2da745f273a2d1408293eada256e5641e&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1279> [image: Image removed by sender.] <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fintent%2Ffavorite%3Fea_u%3D568148082%26ea_e%3D1482574363%26tweet_id%3D807528462227357696%26ea_s%3Db8ef9f10513d3214a0c653856ad943cb042e703b%26cn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=1b6b8e6ebf3d8f80aa17f75c313b8fc95d65b197&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1280> View conversation <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2FXingGao123%2Fstatus%2F807528462227357696%3Fcn%3DbWVudGlvbg%253D%253D%26refsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=bcb78f53aeefd6b7ffb3f0138ae3d35ce18bb712&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1489> *Settings* <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fsettings%2Fnotifications%3Fcn%3DbWVudGlvbg%253D%253D&t=1&cn=bWVudGlvbg%3D%3D&sig=b958a8fd266b036c3fff1b2f9a5ec77dc8f71a5b&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+27> ¦ *Help* <https://twitter.com/i/redirect?url=https%3A%2F%2Fsupport.twitter.com%3Fcn%3DbWVudGlvbg%253D%253D&t=1&cn=bWVudGlvbg%3D%3D&sig=d424d05848153f7b7e051e1899ec783738c2f354&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+97> ¦ *Opt-out* <https://twitter.com/i/u?t=1&cn=bWVudGlvbg%3D%3D&sig=22bcc7dd4f15e69fb439006475d009aa4f6ab7b8&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+26> ¦ *Download app* <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2Fdownload%3Fcn%3DbWVudGlvbg%253D%253D&t=1&cn=bWVudGlvbg%3D%3D&sig=f17dec02c135443518b4b62d33a44e770197677e&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+108> Twitter, Inc. 1355 Market Street, Suite 900 San Francisco, CA 94103 <https://twitter.com/i/redirect?url=https%3A%2F%2Ftwitter.com%2F%3Frefsrc%3Demail&t=1&cn=bWVudGlvbg%3D%3D&sig=aeb213f36b9963d03fd40048a3e379b1d1aef801&iid=76f306c04fed4efaab0d16226f05763a&uid=568148082&nid=4+1553> DISCLAIMER: This communication (including any attachments) is intended for the use of the addressee only and may contain confidential, privileged or copyright material. It may not be relied upon or disclosed to any other person without the consent of The Royal Society of Chemistry. If you have received it in error, you must not copy or show it to anyone; please contact us immediately by replying to this email and highlighting the error. Any advice given by The Royal Society of Chemistry has been carefully formulated but is necessarily based on the information available, and The Royal Society of Chemistry cannot be held responsible for accuracy or completeness. In this respect, any views or opinions presented in this email are solely those of the author and may not represent those of The Royal Society of Chemistry. The Royal Society of Chemistry owes no duty of care and shall not be liable for any resulting damage or loss as a result of the use of this email and/or attachments. The Royal Society of Chemistry acknowledges that a disclaimer cannot restrict liability at law for personal injury or death arising through a finding of negligence. The Royal Society of Chemistry does not warrant that its emails or attachments are Virus-free: Please rely on your own screening. The Royal Society of Chemistry is a charity, registered in England and Wales, Number 207890, and a company incorporated in England by Royal Charter (Registered No. RC000524) Registered office: Burlington House, Piccadilly, London W1J 0BA, Telephone: 0207 4378 6556, Facsimile: 0207 4490 3393 (Head Office). |  |  |  |  | 57 | https://trello.com/c/BsGChunE
Done | **T009a** Warnings during compilation (using gcc 6.2.1) | **T009** ---------- Forwarded message ---------- From: *Dominik 'Rathann' Mierzejewski* <dominik@greysector.net> Date: Tuesday, October 11, 2016 Subject: InChI Software version 1.05 To: inchi-discuss@lists.sourceforge.net Dear Alan, On Thursday, 06 October 2016 at 10:52, Alan McNaught wrote: > InChI Software version 1.05 is now available for review, from the InChI > Trust website: > > http://www.inchi-trust.org/downloads105/ [...] > Comments by Friday November 4th, please. There are a lot of warnings during compilation (using gcc 6.2.1), some of which might indicate programming errors and may lead to crashes. For example: ../../../../INCHI_BASE/src/runichi3.c: In function 'OrigAtData_FillAtProps': ../../../../INCHI_BASE/src/runichi3.c:2455:9: warning: this 'for' clause does not guard... [-Wmisleading-indentation] for (i=0; i<nrings; i++); ^~~ ../../../../INCHI_BASE/src/runichi3.c:2456:9: note: ...this statement, but the latter is misleadingly indented as if it is guarded by the 'for' { ^ This looks like an unintended ';' at the end of line 2455. There are several warnings about implicit declaration of memicmp, which mean missing #include "ichicomp.h". Another example: ./src/e_0dstereo.c: In function 'set_0D_stereo_parities': ../src/e_0dstereo.c:2744:15: warning: 'rmin' may be used uninitialized in this function [-Wmaybe-uninitialized] if ( rmin / rmax < MIN_SINE ) { ~~~~~^~~~~~ ../src/e_0dstereo.c:2629:34: note: 'rmin' was declared here double bond_len_xy[4], rmax, rmin; ^~~~ ../src/e_0dstereo.c:2744:15: warning: 'rmax' may be used uninitialized in this function [-Wmaybe-uninitialized] if ( rmin / rmax < MIN_SINE ) { ~~~~~^~~~~~ ../src/e_0dstereo.c:2629:28: note: 'rmax' was declared here double bond_len_xy[4], rmax, rmin; ^~~~ This might lead to a division by 0 if rmax is 0. rmax and rmin will be 0 if j1 is 0 (line 2730). j1 will be 0 if at[cur_at].num_bonds is 0 (line 2698). I don't know if the last case is possible, but neither does gcc. There are many more and I'm attaching a more complete log of inchi build from Fedora. I patched the Makefile to allow setting compiler flags from the command line. Regards, Dominik -- Fedora http://fedoraproject.org/wiki/User:Rathann RPMFusion http://rpmfusion.org "Faith manages." -- Delenn to Lennier in Babylon 5:"Confessions and Lamentations" |  |  |  | yellow,purple | 31 | https://trello.com/c/NPjMfrDp
Done | **T010** 2) avoid the use of msvc-specific functions like stricmp and memicmp. (Evan Bolton on 2016-10-08) | **T010** |  |  |  | yellow,blue | 6 | https://trello.com/c/qSfJoCcM
Done | Документировать правила ре-канонизации SRU (inchi2struct); update Table and text in TechMan and RelNotes |  |  |  |  | green,purple | 44 | https://trello.com/c/NYrsHpdG
Done | **T008** Needs attention - Burt Leland's fix status check from GetStructFromINCHIEx() | **T008** ---------- Forwarded message ---------- From: *Burt Leland* <bleland@eyesopen.com> Date: Tuesday, October 11, 2016 Subject: InChI Software version 1.05 To: Igor Pletnev <igor.pletnev@gmail.com> Igor, Also, I’m not happy with my Fix status check from GetStructFromINCHIEx() fix – you should look at this in more detail. None of my tests would exercise the “other” status returns, so I simply ensured the “OK” status would continue. The FATAL checking gave me pause…. --burt *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com <javascript:_e(%7B%7D,'cvml','igor.pletnev@gmail.com');>] *Sent:* Tuesday, October 11, 2016 11:01 AM *To:* Burt Leland <bleland@eyesopen.com <javascript:_e(%7B%7D,'cvml','bleland@eyesopen.com');>> *Cc:* Alan McNaught <mcnaught@ntlworld.com <javascript:_e(%7B%7D,'cvml','mcnaught@ntlworld.com');>>; inchi-discuss@lists.sourceforge.net <javascript:_e(%7B%7D,'cvml','inchi-discuss@lists.sourceforge.net');> *Subject:* Re: [InChI-discuss] InChI Software version 1.05 Burt, many thanks for your patch. Regards, Igor On Mon, Oct 10, 2016 at 11:56 PM, Burt Leland <bleland@eyesopen.com <javascript:_e(%7B%7D,'cvml','bleland@eyesopen.com');>> wrote: All, I’ve attached a .patch file of minor code alterations to be considered for the final release. Among the changes: · Move mode.h include *above* check for COMPILE_ANSI_ONLY · Avoid nested /* */ comments – for some platforms (with warning-as-error), these are rejected · Previously submitted *N.Boyle* fix for 0D conversions (loss of stereo) · Fix status check from GetStructFromINCHIEx() ------------------------------------------------------------ ------------------ Check out the vibrant tech community on one of the world's most engaging tech sites, SlashDot.org! http://sdm.link/slashdot _______________________________________________ InChI-discuss mailing list InChI-discuss@lists.sourceforge.net <javascript:_e(%7B%7D,'cvml','InChI-discuss@lists.sourceforge.net');> https://lists.sourceforge.net/lists/listinfo/inchi-discuss |  |  |  | yellow,purple | 25 | https://trello.com/c/noyqhpuu
Done | Audio recording @ Moscow Проверить, что inchi2mol works with DOS-eol'ed input files | Evernote helps you remember everything and get organized effortlessly. [Download Evernote](https://www.evernote.com/getit?utm_source=service&utm_medium=email&utm_content=emailNote&email_name=emailNote&email_guid=94e9d5a7-21cc-496b-bdda-825b377d20c4&email_link=download_app). |  |  |  |  | 60 | https://trello.com/c/bIYeafkT
Done | Audio recording @ Moscow Проверить коды возврата GetStructFromINCHI, .. | Evernote helps you remember everything and get organized effortlessly. [Download Evernote](https://www.evernote.com/getit?utm_source=service&utm_medium=email&utm_content=emailNote&email_name=emailNote&email_guid=9d2c1635-1879-494b-90c5-e6a660ad74c3&email_link=download_app). |  |  |  |  | 59 | https://trello.com/c/PfqiDRLD
Done | **T020** Re-calc polymer examples and update docs after fixing bug in code establishing seniority of atoms in SRU |  |  |  |  | green,purple | 56 | https://trello.com/c/q5Rh5Oee
Done | ** T019** K. Taylor - one more issue w. Large Structures in v1.05 | ---------- Forwarded message ---------- From: Keith Taylor <keith.taylor@laderaconsultancy.com> Date: Mon, Nov 28, 2016 at 4:16 PM Subject: RE: Large Structures in v1.05 To: Igor Pletnev <igor.pletnev@gmail.com> Cc: Evan Bolton <evan@inchi-trust.org>, Alan McNaught <mcnaught@ntlworld.com>, Steve Heller <steve@hellers.com> All but one of my tests has been successful. I tried a robustness test using a large polynucleotide. I have attached the molfile. I manually edited out the Sgroup data and as far as I can tell it is clean. The edited molfile is attached. This one fails with the error message: message: type="fatal (aborted)" value="Cannot interpret V3000 counts line: COUNTS 30772 34477 1511 0 1" This was not an issue with other files that I have manually edited. Once I have this issue resolved, I will circulate a presentation that summarizes my results. *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com] *Sent:* Saturday, November 19, 2016 9:39 AM *To:* Keith Taylor <keith.taylor@laderaconsultancy.com> *Cc:* Evan Bolton <evan@inchi-trust.org>; Alan McNaught < mcnaught@ntlworld.com>; Steve Heller <steve@hellers.com> *Subject:* Re: Large Structures in v1.05 As I wrote yesterday, I made updated GUI proram winchi-1 for you and placed at shared cloud directory at: https://yadi.sk/d/h8gfapyNymMQE If you could not download it for any reason, *please find winchi-1 executable attached to this letter * (as previously, extension is changed to .bak to pass through Google Mail, so you should rename it back to .exe) Please let me know how the things go. On Sat, Nov 19, 2016 at 11:20 AM, Keith Taylor <keith.taylor@ laderaconsultancy.com> wrote: I have the GUI but it has not been updated. Where do I get the updated version. Keith T Taylor Ladera Consultancy LLC+1 209 221 9415 www.laderaconsultancy.com On Nov 18, 2016 16:52, Igor Pletnev <igor.pletnev@gmail.com> wrote: Sorry, seems that I do not understand > A command line application is not something that I find useful. I need a GUI, and the one that I have doesn't work. How do I update it? I just wrote to you today in my previous letter: "There is (and was) also GUI-enabled counterpart program for Windows, winchi-1.exe Note however that it is not as flexible and does not allow as much fine tuning as inchi-1. ... Anyway, I prepared for you and placed in the the same cloud directory as earlier the program winchi-1 Please download and use it, if you prefer so." Did you download and try this GUI program? Did it work for you? On Fri, Nov 18, 2016 at 6:44 PM, <keith.taylor@laderaconsultancy.com> wrote: A command line application is not something that I find useful. I need a GUI, and the one that I have doesn't work. How do I update it? Sent from my Windows 10 phone *From: *Igor Pletnev <igor.pletnev@gmail.com> *Sent: *Friday, November 18, 2016 13:46 *To: *Keith T Taylor <keith.taylor@laderaconsultancy.com> *Cc: *Steve Heller <steve@hellers.com>; Alan McNaught <mcnaught@ntlworld.com>; Evan Bolton <evan@inchi-trust.org> *Subject: *RE: Large Structures in v1.05 1 inchi-1 _is_ stand-alone executable But it is (and was, in all prev versions) the _command line_ ("console") executable It has no GUI and does not intended to be launched by double click in Windows Explorer; rather, it should be launched from command line with necessary parameters, including name of input file, then it generates InChI/Key and produces output files in working directory (when you double click on it, Windows opens a console session with this executable, the executable sees no input file data and prints out help screen and exits, then Windows closes console screen -- this of course may look as "flashes and exits") 2 There is (and was) also GUI-enabled counterpart program for Windows, winchi-1.exe Note however that it is not as flexible and does not allow as much fine tuning as inchi-1. (Also, inchi-1 it is the "main member" of software distribution as its results are the reference to which all other implementations (e.g., those using API) should be compared with ) 3 Anyway, I prepared for you and placed in the the same cloud directory as earlier the program winchi-1 Please download and use it, if you prefer so. Regards, Igor On Nov 16, 2016 6:18 PM, "Keith Taylor" <keith.taylor@laderaconsultancy.com> wrote: For me inchi-1.exe is not a standalone executable. I double-click on it and it flashes and then exits. *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com] *Sent:* Wednesday, November 16, 2016 2:25 PM *To:* Keith Taylor <keith.taylor@laderaconsultancy.com> *Cc:* Steve Heller <steve@hellers.com>; Alan D. McNaught < mcnaught@ntlworld.com>; Evan Bolton <evan@inchi-trust.org> *Subject:* Re: Large Structures in v1.05 Keith - 1 I do not understand what you ran, why winchi-1.exe? I sent to you (renamed) inchi-1.exe... so I guess it's just a typo... 2 Anyway - all is working on my side. Please look at shared cloud directory at: https://yadi.sk/d/h8gfapyNymMQE Here is all the stuff: inchi-1 executable (the same), your problem file "uncompressed filgrastin.mol", Windows batch file run.cmd to launch inchi-1 with this data file, and 3 just produced output files. As a kind of check, InChIKey is KOKXRWZWQJXBOP-NJDFSSKJBA-N, as is seen from "uncompressed filgrastin.mol.txt" output. 3 Please let me know if you can reproduce this behavior/files which I just produced at my desktop. Regards, Igor On Wed, Nov 16, 2016 at 4:49 PM, Keith Taylor <keith.taylor@ laderaconsultancy.com> wrote: I downloaded this file a renamed it to an EXE in the original directory. I then ran winchi-1.exe and it crashed on the problem structure. Do I need to do anything else to make it run. Keith *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com] *Sent:* Monday, November 14, 2016 9:27 AM *To:* Keith Taylor <keith.taylor@laderaconsultancy.com> *Cc:* Steve Heller <steve@hellers.com>; Alan D. McNaught < mcnaught@ntlworld.com>; Evan Bolton <evan@inchi-trust.org> *Subject:* Re: Large Structures in v1.05 Hi Keith, please find attached the fixed version of inchi-1.exe v. 1.05, 32-bit, suitable for large molecules. It includes the fix for your crash example "uncompressed filgrastin.mol" as well as fixes for some issues reported in inchi-discuss. I did not receive further examples from you, so I hope that this fixed version is OK. If you would like to have any other (64-bit version of inchi-1.exe, InChI dll, Linux versions, or full package with source codes) please let me know. Regards, Igor P.S. The attached file is renamed to .bak to get through Google mail; please just replace the extension to .exe On Sat, Nov 5, 2016 at 4:52 PM, Igor Pletnev <igor.pletnev@gmail.com> wrote: OK To be confident in problems coverage/bugfixing, please send me several more large-molecule "plain V3000" files from your records I have previously tested and got no problems on tens of thousands of protein structures -- but this may have been biased as the V3000 files were produced with OpenBabel from PDB data *> ** Unfortunately it crashes on the earlier ISIS/Draw style file that contains Abbreviation Sgroups. The software ought to ignore these non-structurally important features.* please send me this "earlier ISIS/Draw style file" for analysis also On Friday, November 4, 2016, Keith Taylor <keith.taylor@ laderaconsultancy.com> wrote: Thanks. Once I am confident that olain v3000 format files can be used, I will look at a wider range of structures. Then I can put together requirements to make the approach more user friendly. *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com <igor.pletnev@gmail.com>] *Sent:* Friday, November 4, 2016 3:44 PM *To:* Keith Taylor <keith.taylor@laderaconsultancy.com> *Cc:* Steve Heller <steve@hellers.com>; Alan D. McNaught < mcnaught@ntlworld.com>; Evan Bolton <evan@inchi-trust.org> *Subject:* Re: Large Structures in v1.05 Hi Keith, thanks for testing and reporting. *> First it does not understand the SCSR format but they may have been a design decision. Unfortunately it crashes on the earlier ISIS/Draw style file that contains Abbreviation Sgroups. The software ought * Yes, SCSR is not supported As far as I understand, SCSR is a _further extension_ to V3000 format, and we have just added some limited support of V3000 :) Anyway, I will be looking on this, slightly later *> Pushing my luck, I used an actual structure of filgrastin. Unfortunately this one failed to generate an InChI. I eyeballed the molfile and couldn’t see any obvious errors and it renders fine in BIOVIA Draw.* *> I have attached the files for analysis.* Thanks for the files Will check and fix, then let you know Best regards, Igor On Thu, Nov 3, 2016 at 10:38 PM, Keith Taylor <keith.taylor@ laderaconsultancy.com> wrote: First it does not understand the SCSR format but they may have been a design decision. Unfortunately it crashes on the earlier ISIS/Draw style file that contains Abbreviation Sgroups. The software ought to ignore these non-structurally important features. This is simpler to achieve in the v3000 but can be done in the v2000 format. This makes life very tedious. Removing the Sgroups requires a transition to SMILES then a conversion of the SMILES back to a molfile. I made a peptide from 60 repeats of a gly-ala-phe trimer. This is just enough to trigger the v3000 format. After jumping through the SMILES hoop, I go a good conversion – as far as I can tell. To test it further I make a 100 repeat version and it to converted. Pushing my luck, I used an actual structure of filgrastin. Unfortunately this one failed to generate an InChI. I eyeballed the molfile and couldn’t see any obvious errors and it renders fine in BIOVIA Draw. I have attached the files for analysis. Regards Keith |  |  |  |  | 55 | https://trello.com/c/NwtC199b
Done | **T018** Flag character 'S' appears (sometimes?) instead of 'B' in InChI/Key for LargeMolecules |  |  |  |  | yellow,red | 47 | https://trello.com/c/gitdNCyY
Done | **T017** Make all V3000 file reads via growing buffer rather than array{MAX...LEN] |  |  |  |  | orange,purple | 45 | https://trello.com/c/4VaLGBCM
Done | **T016** For back compatibility: make so that no '*' or 'Zz' elements are allowed in the input to GetINCHI() |  |  |  |  | yellow,purple | 46 | https://trello.com/c/xXYXw2IZ
Done | **T015** Large Structures in v1.05 - bug found by K. Taylor | ---------- Forwarded message ---------- From: Keith Taylor <keith.taylor@laderaconsultancy.com> Date: Thu, Nov 3, 2016 at 10:38 PM Subject: RE: Large Structures in v1.05 To: Steve Heller <steve@hellers.com>, igor.pletnev@gmail.com Cc: "Alan D. McNaught" <mcnaught@ntlworld.com>, Evan Bolton < evan@inchi-trust.org> First it does not understand the SCSR format but they may have been a design decision. Unfortunately it crashes on the earlier ISIS/Draw style file that contains Abbreviation Sgroups. The software ought to ignore these non-structurally important features. This is simpler to achieve in the v3000 but can be done in the v2000 format. This makes life very tedious. Removing the Sgroups requires a transition to SMILES then a conversion of the SMILES back to a molfile. I made a peptide from 60 repeats of a gly-ala-phe trimer. This is just enough to trigger the v3000 format. After jumping through the SMILES hoop, I go a good conversion – as far as I can tell. To test it further I make a 100 repeat version and it to converted. Pushing my luck, I used an actual structure of filgrastin. Unfortunately this one failed to generate an InChI. I eyeballed the molfile and couldn’t see any obvious errors and it renders fine in BIOVIA Draw. I have attached the files for analysis. Regards Keith |  |  |  | yellow,red | 43 | https://trello.com/c/4nK53ogv
Done | Multi-patch from Burt Leland | From: *Burt Leland* <bleland@eyesopen.com> Date: Monday, October 10, 2016 All, I’ve attached a .patch file of minor code alterations to be considered for the final release. Among the changes: · Move mode.h include *above* check for COMPILE_ANSI_ONLY · Avoid nested /* */ comments – for some platforms (with warning-as-error), these are rejected · Previously submitted *N.Boyle* fix for 0D conversions (loss of stereo) · Fix status check from GetStructFromINCHIEx() |  |  |  | red,yellow | 17 | https://trello.com/c/1A0Kyoz7
Done | **T002** GetINCHI bug - 0D stereo is not passed | **T002** ---------- Forwarded message ---------- From: *Noel O'Boyle* <baoilleach@gmail.com> Date: Monday, October 10, 2016 Subject: InChI Software version 1.05 To: Alan McNaught <mcnaught@ntlworld.com> Cc: "inchi-discuss@lists.sourceforge.net" < inchi-discuss@lists.sourceforge.net> Just found a serious regression in GetINCHI that causes segfaults and errors in the Open Babel test suite. The 0D stereo information is not passed through, although the number of 0D stereocenters is. In short, inchi_dll.c is missing the following line in GetINCHI: extended_input.stereo0D = inp->stereo0D; I would very much appreciate if you could add tests for 0D conversion to the your own InChI test suite. Open Babel relies on this for SMILES->InChI conversion, as does (for example) OPSIN for IUPAC Name->InChI conversion. Regards, - Noel On 10 October 2016 at 11:48, John M <john.wilkinsonmay@gmail.com <javascript:;>> wrote: > And again... these ones are now correct... difficult to debug at the moment > as I'm on back so going via SSH and copying back and forth. > >> p[Gly] 1 >> >> InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8, 9)/z101-1,3,6-7(2-6,5-1) >> InChIKey=YMAWOPBAYDPSLA-NPFRMHEKBA-N >> >> p[Gly] 2 >> >> InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8, 9)/z101-2-3,6-7(1-3,4-2) >> InChIKey=YMAWOPBAYDPSLA-LCMLVUGIBA-N >> >> p[Gly] 3 >> >> InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8, 9)/z101-2,4,6,8(3-6,9-4) >> InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N > > > > > ------------------------------------------------------------ ------------------ > Check out the vibrant tech community on one of the world's most > engaging tech sites, SlashDot.org! http://sdm.link/slashdot > _______________________________________________ > InChI-discuss mailing list > InChI-discuss@lists.sourceforge.net <javascript:;> > https://lists.sourceforge.net/lists/listinfo/inchi-discuss > ------------------------------------------------------------ ------------------ Check out the vibrant tech community on one of the world's most engaging tech sites, SlashDot.org! http://sdm.link/slashdot _______________________________________________ InChI-discuss mailing list InChI-discuss@lists.sourceforge.net <javascript:;> https://lists.sourceforge.net/lists/listinfo/inchi-discuss |  |  |  | green,red | 26 | https://trello.com/c/O4LYIPqP
Done | **T012** InChI v. 1.05 - OSX build advice | **T012** From: *Burt Leland* <bleland@eyesopen.com> Date: Tuesday, October 11, 2016 Subject: InChI Software version 1.05 To: Alan McNaught <mcnaught@ntlworld.com>, " inchi-discuss@lists.sourceforge.net" <inchi-discuss@lists.sourceforge.net> For your consideration – another change to (minimally) allow OSX linking - __isascii missing from linker phase, so add the include that provides the #define diff -rcb INCHI-1-SRC\INCHI_BASE\src\util.c .\inchi\util.c *** INCHI-1-SRC\INCHI_BASE\src\util.c Fri Oct 07 11:59:54 2016 --- .\inchi\util.c Mon Oct 10 16:27:25 2016 *************** *** 43,48 **** --- 43,52 ---- #include <ctype.h> #include "mode.h" + #if defined(COMPILE_ANSI_ONLY) && defined(__APPLE__) + /* possibly needed for __isascii define */ + #include "ichicomp.h" + #endif #include "util.h" #include "extr_ct.h" |  |  |  | blue,green | 15 | https://trello.com/c/qdvng938
Done | **T007** InChI Software version 1.05: minor bug in /OUTPUTSDF mode | **T007** ---------- Forwarded message ---------- From: Igor Pletnev <igor.pletnev@gmail.com> Date: Thu, Oct 13, 2016 at 2:35 PM Subject: Re: InChI Software version 1.05: minor bug in /OUTPUTSDF mode To: "Tchekhovskoi, Dmitrii V. Dr. (Fed)" <dmitrii.tchekhovskoi@nist.gov> Dear Dima, thank you, will be fixed. Regards, Igor On Wed, Oct 12, 2016 at 8:34 PM, Tchekhovskoi, Dmitrii V. Dr. (Fed) < dmitrii.tchekhovskoi@nist.gov> wrote: > Dear Igor, > > > > In mol_fmt4.c, lines 906-907 > > > > inchi_ios_print_nodisplay(fcb,"%3d%3d 0 0%3d 0 0 0 0 0%3d%s\n", > > num_atoms, *num_bonds, bChiralFlag?1:0, > *nNumAddLines,nNumAddLines*?" V2000":""); > > > > should be > > > > inchi_ios_print_nodisplay(fcb,"%3d%3d 0 0%3d 0 0 0 0 0%3d%s\n", > > num_atoms, *num_bonds, bChiralFlag?1:0, > **nNumAddLines,*nNumAddLines*?" V2000":""); > > > > because *nNumAddLines* is a pointer. > > > > Regards > > > > Dmitrii > > > |  |  |  | green,purple | 35 | https://trello.com/c/GEkxU5Rt
Done | **T001** Technical manual needs updating, polymers | **T001** ---------- Forwarded message ---------- From: *John M* <john.wilkinsonmay@gmail.com> Date: Monday, October 10, 2016 Subject: InChI Software version 1.05 To: inchi-discuss@lists.sourceforge.net Hi all, Some initial thoughts on the v1.05 release. I've mainly looked at polymers (in Beta) as I guess that's where most problems will be. 1) Technical manual needs updating, a section on polymers has been added but the intro says polymers are out of scope. *"Not included are polymers, molecular class representations (Markush structures), electronic states and conformations."* 2) Phase/frame shifts are not handled with capping groups, example three ways to encode poly-glycine give three different InChIs. *SMILES (click to view)* NCC(=O)NCC(=O)O ¦Sg:n:1,2,3,4:n:ht¦ pGly_1 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A1%2C2%2C3%2C4%3An%3Aht%7C%20pGly_1&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:2,3,4,5:n:ht¦ pGly_2 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A2%2C3%2C4%2C5%3An%3Aht%7C%20pGly_2&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:4,5,6,7:n:ht¦ pGly_3 > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A4%2C5%2C6%2C7%3An%3Aht%7C%20pGly_3&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> *InChI* InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-1,3,6-7(2-6,5-1) > InChIKey=YMAWOPBAYDPSLA-LCMLVUGIBA-N InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2-3,6-7(1-3,4-2) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N > InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2,4,6,8(3-6,9-4) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N 3) Different size repeats (no capping groups) don't produce comparable InChIs. Possibly out of scope but below PEG_n (odd or even) should match PEG_2n (even only), PEG_2n should not match PEG_n. I'd imagine this should be possible with more layers within the polymer layer... *CCO* ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCOCCO* > ¦Sg:n:1,2,3,4,5,6:n:ht,$_AP1;;;;;;;_AP1$¦ PEG_2n > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCOCCO*%20%7CSg%3An%3A1%2C2%2C3%2C4%2C5%2C6%3An%3Aht%2C%24_AP1%3B%3B%3B%3B%3B%3B%3B_AP1%24%7C%20PEG_2n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N > InChI=1B/C4H8O2/c1-2-6-4-3-5-1/h1-4H2/z101-1-6(1,2,1,5,2,6,3,4,3,5,4,6) > InChIKey=RYHBNJHYFVUHQT-UEXHMUNTBA-N 4) Attachment points (M APO in ctab) are not handled but could be used in place of star atoms. *CCO* ¦Sg:n:1,2,3:n:ht¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCO* > ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n_ap > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n_ap&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N InChI=1B/C2H6O/c1-2-3/h3H,2H2,1H3/z200-1-3 > InChIKey=LFQSCWFLJHTTHZ-DJNVOPQRBA-N - John |  |  |  | green,red | 23 | https://trello.com/c/8X6Bn3BG
Done | **T005** 1) gcc requires explicit casts of void* to whatever variable is being assigned to the result of inchi_calloc (Evan Bolton on 2016-10-08) | **T005** |  |  |  | green,purple | 4 | https://trello.com/c/GRCYh4aT
Done | **T004** (type) cast (for example, (int*) inchi_malloc(…), etc.) | **T004** ---------- Forwarded message ---------- From: Tchekhovskoi, Dmitrii V. Dr. (Fed) <dmitrii.tchekhovskoi@nist.gov> Date: Fri, Oct 14, 2016 at 3:25 PM Subject: InChI v.1.05 and COMPILE_ALL_CPP=1 To: "Igor Pletnev (igor.pletnev@gmail.com)" <igor.pletnev@gmail.com> Dear Igor, Setting COMPILE_ALL_CPP=1 in inchi-1 project and rebuilding inchi-1.exe with C++ compiler by setting inchi-1//Properties//inchi-1 Property Pages//Configuration Properties//C/C++//Advanced//Compile As = Compile as C++ Code(/TP) produces several errors because inchi_malloc(…) and inchi_calloc(…) return void* pointers, which C++ refuses to assign to pointers of type int*, char*, etc. Adding a simple (type) cast (for example, (int*) inchi_malloc(…), etc.) resolves the issue. I haven’t tried to rebuild inchi dll and inchi_main with C++ compiler. Regards Dmitrii |  |  |  | purple,green | 39 | https://trello.com/c/O40cqVX8
Done | Colin Batchelor - write on 0D-stereo tests |  |  |  |  | yellow,purple | 42 | https://trello.com/c/A1j9OtWx
Done | Adding those tests for 0D-stereo data to the test suite? | ---------- Forwarded message ---------- From: Colin Batchelor <batchelorc@rsc.org> Date: Wed, Oct 12, 2016 at 12:32 PM Subject: RE: [InChI-discuss] InChI Software version 1.05 To: Igor Pletnev <igor.pletnev@gmail.com>, Noel O'Boyle < baoilleach@gmail.com>, Alan McNaught <mcnaught@ntlworld.com> Cc: "inchi-discuss@lists.sourceforge.net" < inchi-discuss@lists.sourceforge.net> Hello Igor, Will you be adding those tests for 0D-stereo data to the test suite? Best wishes, Colin. *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com] *Sent:* 11 October 2016 17:22 *To:* Noel O'Boyle; Alan McNaught *Cc:* inchi-discuss@lists.sourceforge.net *Subject:* Re: [InChI-discuss] InChI Software version 1.05 > Just found a serious regression in GetINCHI that causes segfaults and Thanks for finding and reporting the bug. > inchi_dll.c is missing the following line in GetINCHI: > extended_input.stereo0D = inp->stereo0D; Yes, it is correct. > I would very much appreciate if you could add tests for 0D conversion Yes. Specific tests for 0D-stereo data will be performed before final release. In the meantime, could you please let us know: did your tests finally pass after fixing the line above? Regards, Igor 10/10/2016 4:56 PM, Noel O'Boyle пишет: Just found a serious regression in GetINCHI that causes segfaults and errors in the Open Babel test suite. The 0D stereo information is not passed through, although the number of 0D stereocenters is. In short, inchi_dll.c is missing the following line in GetINCHI: extended_input.stereo0D = inp->stereo0D; I would very much appreciate if you could add tests for 0D conversion to the your own InChI test suite. Open Babel relies on this for SMILES->InChI conversion, as does (for example) OPSIN for IUPAC Name->InChI conversion. Regards, - Noel On 10 October 2016 at 11:48, John M <john.wilkinsonmay@gmail.com> <john.wilkinsonmay@gmail.com> wrote: And again... these ones are now correct... difficult to debug at the moment as I'm on back so going via SSH and copying back and forth. p[Gly] 1 InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9)/z101-1,3,6-7(2-6,5-1) InChIKey=YMAWOPBAYDPSLA-NPFRMHEKBA-N p[Gly] 2 InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9)/z101-2-3,6-7(1-3,4-2) InChIKey=YMAWOPBAYDPSLA-LCMLVUGIBA-N p[Gly] 3 InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9)/z101-2,4,6,8(3-6,9-4) InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N ------------------------------------------------------------------------------ Check out the vibrant tech community on one of the world's most engaging tech sites, SlashDot.org! http://sdm.link/slashdot _______________________________________________ InChI-discuss mailing list InChI-discuss@lists.sourceforge.net https://lists.sourceforge.net/lists/listinfo/inchi-discuss ------------------------------------------------------------------------------ Check out the vibrant tech community on one of the world's most engaging tech sites, SlashDot.org! http://sdm.link/slashdot _______________________________________________ InChI-discuss mailing list InChI-discuss@lists.sourceforge.net https://lists.sourceforge.net/lists/listinfo/inchi-discuss DISCLAIMER: This communication (including any attachments) is intended for the use of the addressee only and may contain confidential, privileged or copyright material. It may not be relied upon or disclosed to any other person without the consent of The Royal Society of Chemistry. If you have received it in error, you must not copy or show it to anyone; please contact us immediately by replying to this email and highlighting the error. Any advice given by The Royal Society of Chemistry has been carefully formulated but is necessarily based on the information available, and The Royal Society of Chemistry cannot be held responsible for accuracy or completeness. In this respect, any views or opinions presented in this email are solely those of the author and may not represent those of The Royal Society of Chemistry. The Royal Society of Chemistry owes no duty of care and shall not be liable for any resulting damage or loss as a result of the use of this email and/or attachments. The Royal Society of Chemistry acknowledges that a disclaimer cannot restrict liability at law for personal injury or death arising through a finding of negligence. The Royal Society of Chemistry does not warrant that its emails or attachments are Virus-free: Please rely on your own screening. The Royal Society of Chemistry is a charity, registered in England and Wales, Number 207890, and a company incorporated in England by Royal Charter (Registered No. RC000524) Registered office: Burlington House, Piccadilly, London W1J 0BA, Telephone: 0207 4378 6556, Facsimile: 0207 4490 3393 (Head Office). |  |  |  | yellow,red | 34 | https://trello.com/c/JiUQswVC
Done | Galina Gladkova? |  |  |  |  | red,yellow | 29 | https://trello.com/c/qUt15Q1N
Done | Start new repo with v. 1.05 pre-release or just go with huge commit to INCHI-DEV and sync further changes there |  |  |  |  | red,yellow | 16 | https://trello.com/c/k7EQcHhb
Done | **T003** Possible empty loop in runichi3.c | **T003** ---------- Forwarded message ---------- From: *Linstrom, Peter (Fed)* <peter.linstrom@nist.gov> Date: Thursday, October 13, 2016 Subject: Possible empty loop in runichi3.c To: "Igor Pletnev (igor.pletnev@gmail.com)" <igor.pletnev@gmail.com> Cc: "Tchekhovskoi, Dmitrii V. Dr. (Fed)" <dmitrii.tchekhovskoi@nist.gov> Igor, I’ve just started to look at the new InChI code and I came across the following on lines 2455 to 2470 in runichi3.c: for (i=0; i<nrings; i++)*;* { int erank, max_erank = 0; for (k=0; k<nat; k++) { if ( aprops[k].ring_num == i ) { erank = erank_rule2[ at[k].el_number ]; if ( erank > max_erank ) max_erank = erank; } } for (k=0; k<nat; k++) if ( aprops[k].ring_num == i ) aprops[k].ring_erank = max_erank; } If I’m reading this code correctly it looks like the semicolon at the end of the first line means that the remaining code only gets executed once (with i = nrings). Is the semicolon a typo? Peter ==================================== Peter J. Linstrom (301) 975-5422 NIST, Office of Data and Informatics ==================================== |  |  |  | green,red | 37 | https://trello.com/c/zwFrsJrU
Done | Написать Доминику Мержевскому и Питеру Линстрому вежливую благодарность(указав на отн малознач-сть) | Igor, I just realized my comment is a duplicate of the message by Dominik 'Rathann' Mierzejewski to the InChI-discuss mailing list dated October 11. I should have checked the mailing list more carefully before sending it to you. Peter From: Linstrom, Peter (Fed) Sent: Thursday, October 13, 2016 4:49 PM To: Igor Pletnev (igor.pletnev@gmail.com) <igor.pletnev@gmail.com> Cc: Tchekhovskoi, Dmitrii V. Dr. (dmitrii.tchekhovskoi@nist.gov) <dmitrii.tchekhovskoi@nist.gov> Subject: Possible empty loop in runichi3.c Igor, I’ve just started to look at the new InChI code and I came across the following on lines 2455 to 2470 in runichi3.c: for (i=0; i<nrings; i++); { int erank, max_erank = 0; for (k=0; k<nat; k++) { if ( aprops[k].ring_num == i ) { erank = erank_rule2[ at[k].el_number ]; if ( erank > max_erank ) max_erank = erank; } } for (k=0; k<nat; k++) if ( aprops[k].ring_num == i ) aprops[k].ring_erank = max_erank; } If I’m reading this code correctly it looks like the semicolon at the end of the first line means that the remaining code only gets executed once (with i = nrings). Is the semicolon a typo? Peter ==================================== Peter J. Linstrom (301) 975-5422 NIST, Office of Data and Informatics ==================================== |  |  |  | green,red | 36 | https://trello.com/c/JmcldrBK
Done | Написать Барту ответ (thnx for ChEMBL tests) |  |  |  |  | green,red | 40 | https://trello.com/c/29js3IRo
Done | Cleanest way to validate Structure > InChi > Structure (round-trip) | ---------- Forwarded message ---------- From: *Burt Leland* <bleland@eyesopen.com> Date: Wednesday, October 12, 2016 Subject: InChI Software version 1.05 To: Igor Pletnev <igor.pletnev@gmail.com> Igor, I’m trying to find the cleanest way to validate Structure > InChi > Structure, i.e,. that a round-trip is 100% accurate. Is the proper way something like, inchi-1.exe ProbeStructures.sdf inchi-1.exe ProbeStructures.sdf.txt /Inchi2Inchi where I presume the last step is InChI>Structure>Inchi(*) and validation of InChI == InChI(*) ? On Tuesday, October 11, 2016, Burt Leland <bleland@eyesopen.com <javascript:_e(%7B%7D,'cvml','bleland@eyesopen.com');>> wrote: Igor, Also, I’m not happy with my Fix status check from GetStructFromINCHIEx() fix – you should look at this in more detail. None of my tests would exercise the “other” status returns, so I simply ensured the “OK” status would continue. The FATAL checking gave me pause…. --burt *From:* Igor Pletnev [mailto:igor.pletnev@gmail.com] *Sent:* Tuesday, October 11, 2016 11:01 AM *To:* Burt Leland <bleland@eyesopen.com> *Cc:* Alan McNaught <mcnaught@ntlworld.com>; inchi-discuss@lists. sourceforge.net *Subject:* Re: [InChI-discuss] InChI Software version 1.05 Burt, many thanks for your patch. Regards, Igor On Mon, Oct 10, 2016 at 11:56 PM, Burt Leland <bleland@eyesopen.com> wrote: All, I’ve attached a .patch file of minor code alterations to be considered for the final release. Among the changes: · Move mode.h include *above* check for COMPILE_ANSI_ONLY · Avoid nested /* */ comments – for some platforms (with warning-as-error), these are rejected · Previously submitted *N.Boyle* fix for 0D conversions (loss of stereo) · Fix status check from GetStructFromINCHIEx() ------------------------------------------------------------ ------------------ Check out the vibrant tech community on one of the world's most engaging tech sites, SlashDot.org! http://sdm.link/slashdot _______________________________________________ InChI-discuss mailing list InChI-discuss@lists.sourceforge.net https://lists.sourceforge.net/lists/listinfo/inchi-discuss |  |  |  | green,purple | 32 | https://trello.com/c/mAwVEEI7
Done | Save HG snapshot for published pre-release sources and arc whole INCHI-DEV snapshot |  |  |  |  | green,red | 12 | https://trello.com/c/twkDtGQM
Done | SourceForge bug tracker (написать Алану/Стиву) | Посмотреть старую почту и написать Алану/Стиву; потом, может быть, ответить в InChI-discuss |  |  |  | yellow,purple | 14 | https://trello.com/c/iEGOcHza
Done | ** NOT A BUG ** Phase/frame shifts are not handled with capping groups | ---------- Forwarded message ---------- From: *John M* <john.wilkinsonmay@gmail.com> Date: Monday, October 10, 2016 Subject: InChI Software version 1.05 To: inchi-discuss@lists.sourceforge.net Hi all, Some initial thoughts on the v1.05 release. I've mainly looked at polymers (in Beta) as I guess that's where most problems will be. 1) Technical manual needs updating, a section on polymers has been added but the intro says polymers are out of scope. *"Not included are polymers, molecular class representations (Markush structures), electronic states and conformations."* 2) Phase/frame shifts are not handled with capping groups, example three ways to encode poly-glycine give three different InChIs. *SMILES (click to view)* NCC(=O)NCC(=O)O ¦Sg:n:1,2,3,4:n:ht¦ pGly_1 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A1%2C2%2C3%2C4%3An%3Aht%7C%20pGly_1&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:2,3,4,5:n:ht¦ pGly_2 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A2%2C3%2C4%2C5%3An%3Aht%7C%20pGly_2&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:4,5,6,7:n:ht¦ pGly_3 > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A4%2C5%2C6%2C7%3An%3Aht%7C%20pGly_3&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> *InChI* InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-1,3,6-7(2-6,5-1) > InChIKey=YMAWOPBAYDPSLA-LCMLVUGIBA-N InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2-3,6-7(1-3,4-2) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N > InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2,4,6,8(3-6,9-4) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N 3) Different size repeats (no capping groups) don't produce comparable InChIs. Possibly out of scope but below PEG_n (odd or even) should match PEG_2n (even only), PEG_2n should not match PEG_n. I'd imagine this should be possible with more layers within the polymer layer... *CCO* ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCOCCO* > ¦Sg:n:1,2,3,4,5,6:n:ht,$_AP1;;;;;;;_AP1$¦ PEG_2n > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCOCCO*%20%7CSg%3An%3A1%2C2%2C3%2C4%2C5%2C6%3An%3Aht%2C%24_AP1%3B%3B%3B%3B%3B%3B%3B_AP1%24%7C%20PEG_2n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N > InChI=1B/C4H8O2/c1-2-6-4-3-5-1/h1-4H2/z101-1-6(1,2,1,5,2,6,3,4,3,5,4,6) > InChIKey=RYHBNJHYFVUHQT-UEXHMUNTBA-N 4) Attachment points (M APO in ctab) are not handled but could be used in place of star atoms. *CCO* ¦Sg:n:1,2,3:n:ht¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCO* > ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n_ap > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n_ap&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N InChI=1B/C2H6O/c1-2-3/h3H,2H2,1H3/z200-1-3 > InChIKey=LFQSCWFLJHTTHZ-DJNVOPQRBA-N - John |  |  |  | green,blue | 21 | https://trello.com/c/4hRecag9
Done | ** NOT A BUG ** Different size repeats (no capping groups) don't produce comparable InChIs | ---------- Forwarded message ---------- From: *John M* <john.wilkinsonmay@gmail.com> Date: Monday, October 10, 2016 Subject: InChI Software version 1.05 To: inchi-discuss@lists.sourceforge.net Hi all, Some initial thoughts on the v1.05 release. I've mainly looked at polymers (in Beta) as I guess that's where most problems will be. 1) Technical manual needs updating, a section on polymers has been added but the intro says polymers are out of scope. *"Not included are polymers, molecular class representations (Markush structures), electronic states and conformations."* 2) Phase/frame shifts are not handled with capping groups, example three ways to encode poly-glycine give three different InChIs. *SMILES (click to view)* NCC(=O)NCC(=O)O ¦Sg:n:1,2,3,4:n:ht¦ pGly_1 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A1%2C2%2C3%2C4%3An%3Aht%7C%20pGly_1&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:2,3,4,5:n:ht¦ pGly_2 > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A2%2C3%2C4%2C5%3An%3Aht%7C%20pGly_2&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>NCC(=O)NCC(=O)O > ¦Sg:n:4,5,6,7:n:ht¦ pGly_3 > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=NCC(=O)NCC(=O)O%20%7CSg%3An%3A4%2C5%2C6%2C7%3An%3Aht%7C%20pGly_3&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> *InChI* InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-1,3,6-7(2-6,5-1) > InChIKey=YMAWOPBAYDPSLA-LCMLVUGIBA-N InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2-3,6-7(1-3,4-2) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N > InChI=1B/C4H8N2O3/c5-1-3(7)6-2-4(8)9/h1-2,5H2,(H,6,7)(H,8,9) > /z101-2,4,6,8(3-6,9-4) > InChIKey=YMAWOPBAYDPSLA-YYSJEQPSBA-N 3) Different size repeats (no capping groups) don't produce comparable InChIs. Possibly out of scope but below PEG_n (odd or even) should match PEG_2n (even only), PEG_2n should not match PEG_n. I'd imagine this should be possible with more layers within the polymer layer... *CCO* ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCOCCO* > ¦Sg:n:1,2,3,4,5,6:n:ht,$_AP1;;;;;;;_AP1$¦ PEG_2n > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCOCCO*%20%7CSg%3An%3A1%2C2%2C3%2C4%2C5%2C6%3An%3Aht%2C%24_AP1%3B%3B%3B%3B%3B%3B%3B_AP1%24%7C%20PEG_2n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N > InChI=1B/C4H8O2/c1-2-6-4-3-5-1/h1-4H2/z101-1-6(1,2,1,5,2,6,3,4,3,5,4,6) > InChIKey=RYHBNJHYFVUHQT-UEXHMUNTBA-N 4) Attachment points (M APO in ctab) are not handled but could be used in place of star atoms. *CCO* ¦Sg:n:1,2,3:n:ht¦ PEG_n > > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%7C%20PEG_n&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none>*CCO* > ¦Sg:n:1,2,3:n:ht,$_AP1;;;;_AP1$¦ PEG_n_ap > <https://cdkdepict-openchem.rhcloud.com/depict/bow/svg?smi=*CCO*%20%7CSg%3An%3A1%2C2%2C3%3An%3Aht%2C%24_AP1%3B%3B%3B%3B_AP1%24%7C%20PEG_n_ap&abbr=off&suppressh=true&showtitle=true&zoom=1.3&annotate=none> > InChI=1B/C2H4O/c1-2-3-1/h1-2H2/z101-1-3(1,2,1,3,2,3) > InChIKey=IAYPIBMASNFSPL-GCGQHNKHBA-N InChI=1B/C2H6O/c1-2-3/h3H,2H2,1H3/z200-1-3 > InChIKey=LFQSCWFLJHTTHZ-DJNVOPQRBA-N - John |  |  |  | green,blue | 22 | https://trello.com/c/iWbvPGao

## Archived InChI v. 1.05
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Pre-release: bugs reported | [archived] InChI Certification Suite |  |  |  |  | orange | 1 | https://trello.com/c/Nc7ZBoGY
Pre-release: bugs reported | [archived] Test and update | [5 empty] | 2 | https://trello.com/c/HaugOR3T
Pre-release: feature requests | [archived] consider prior to rollout: | [5 empty] | 5 | https://trello.com/c/qGWeAoyD